## --UNIT TESTING
Proponent | Module Name | Unit Name | Date Tested | Test Case ID | Test Case Description | Expected Result | Actual Result | Result | STATUS | NOTE
Villamor, AJ | Account Management | Login | 2025-10-31 | CASE-001 | User enters invalid input | Fails with error message | Performed as expected | Passed | True
Villamor, AJ | Account Management | Login | 2025-10-31 | CASE-002 | User leaves required field empty | Fails with error message | Performed as expected | Passed | True
Villamor, AJ | Account Management | Login | 2025-10-31 | CASE-003 | User enters valid data | Operation successful | Performed as expected | Passed | True
Villamor, AJ | Account Management | Registration | 2025-10-31 | CASE-004 | User enters invalid input | Fails with error message | Performed as expected | Passed | True
Villamor, AJ | Account Management | Registration | 2025-10-31 | CASE-005 | User leaves required field empty | Fails with error message | Performed as expected | Passed | True
Villamor, AJ | Account Management | Registration | 2025-10-31 | CASE-006 | User enters valid data | Operation successful | Performed as expected | Passed | True
Villamor, AJ | Account Management | Profile Update | 2025-10-31 | CASE-007 | User enters invalid input | Fails with error message | Performed as expected | Passed | True
Villamor, AJ | Account Management | Profile Update | 2025-10-31 | CASE-008 | User leaves required field empty | Fails with error message | Performed as expected | Passed | True
Villamor, AJ | Account Management | Profile Update | 2025-10-31 | CASE-009 | User enters valid data | Operation successful | Performed as expected | Passed | True
Villamor, AJ | Job Management | Post Job | 2025-10-31 | CASE-010 | User enters invalid input | Fails with error message | Performed as expected | Passed | True
Villamor, AJ | Job Management | Post Job | 2025-10-31 | CASE-011 | User leaves required field empty | Fails with error message | Performed as expected | Passed | True
Villamor, AJ | Job Management | Post Job | 2025-10-31 | CASE-012 | User enters valid data | Operation successful | Performed as expected | Passed | True
Villamor, AJ | Job Management | Edit Job | 2025-10-31 | CASE-013 | User enters invalid input | Fails with error message | Performed as expected | Passed | True
Villamor, AJ | Job Management | Edit Job | 2025-10-31 | CASE-014 | User leaves required field empty | Fails with error message | Performed as expected | Passed | True
Villamor, AJ | Job Management | Edit Job | 2025-10-31 | CASE-015 | User enters valid data | Operation successful | Performed as expected | Passed | True
Villamor, AJ | Job Management | View Job Listings | 2025-10-31 | CASE-016 | User enters invalid input | Fails with error message | Performed as expected | Passed | True
Villamor, AJ | Job Management | View Job Listings | 2025-10-31 | CASE-017 | User leaves required field empty | Fails with error message | Performed as expected | Passed | True
Villamor, AJ | Job Management | View Job Listings | 2025-10-31 | CASE-018 | User enters valid data | Operation successful | Performed as expected | Passed | True
Abordo, Nykrow | Bidding Module | Submit Bid | 2025-10-31 | CASE-019 | User enters invalid input | Fails with error message | Performed as expected | Passed | True
Abordo, Nykrow | Bidding Module | Submit Bid | 2025-10-31 | CASE-020 | User leaves required field empty | Fails with error message | Performed as expected | Passed | True
Abordo, Nykrow | Bidding Module | Submit Bid | 2025-10-31 | CASE-021 | User enters valid data | Operation successful | Performed as expected | Passed | True
Abordo, Nykrow | Bidding Module | Manage Proposals | 2025-10-31 | CASE-022 | User enters invalid input | Fails with error message | Performed as expected | Passed | True
Abordo, Nykrow | Bidding Module | Manage Proposals | 2025-10-31 | CASE-023 | User leaves required field empty | Fails with error message | Performed as expected | Passed | True
Abordo, Nykrow | Bidding Module | Manage Proposals | 2025-10-31 | CASE-024 | User enters valid data | Operation successful | Performed as expected | Passed | True
Abordo, Nykrow | Contract and Payment Management | Create Contract | 2025-10-31 | CASE-025 | User enters invalid input | Fails with error message | Performed as expected | Passed | True
Abordo, Nykrow | Contract and Payment Management | Create Contract | 2025-10-31 | CASE-026 | User leaves required field empty | Fails with error message | Performed as expected | Passed | True
Abordo, Nykrow | Contract and Payment Management | Create Contract | 2025-10-31 | CASE-027 | User enters valid data | Operation successful | Performed as expected | Passed | True
Abordo, Nykrow | Contract and Payment Management | Update Contract Status | 2025-10-31 | CASE-028 | User enters invalid input | Fails with error message | Performed as expected | Passed | True
Abordo, Nykrow | Contract and Payment Management | Update Contract Status | 2025-10-31 | CASE-029 | User leaves required field empty | Fails with error message | Performed as expected | Passed | True
Abordo, Nykrow | Contract and Payment Management | Update Contract Status | 2025-10-31 | CASE-030 | User enters valid data | Operation successful | Performed as expected | Passed | True
Abordo, Nykrow | Contract and Payment Management | Payment Processing | 2025-10-31 | CASE-031 | User enters invalid input | Fails with error message | Performed as expected | Passed | True
Abordo, Nykrow | Contract and Payment Management | Payment Processing | 2025-10-31 | CASE-032 | User leaves required field empty | Fails with error message | Performed as expected | Passed | True
Abordo, Nykrow | Contract and Payment Management | Payment Processing | 2025-10-31 | CASE-033 | User enters valid data | Operation successful | Performed as expected | Passed | True
Villamor, AJ | Review and Messaging | Submit Review | 2025-10-31 | CASE-034 | User enters invalid input | Fails with error message | Performed as expected | Passed | True
Villamor, AJ | Review and Messaging | Submit Review | 2025-10-31 | CASE-035 | User leaves required field empty | Fails with error message | Performed as expected | Passed | True
Villamor, AJ | Review and Messaging | Submit Review | 2025-10-31 | CASE-036 | User enters valid data | Operation successful | Performed as expected | Passed | True
Villamor, AJ | Review and Messaging | View Feedback | 2025-10-31 | CASE-037 | User enters invalid input | Fails with error message | Performed as expected | Passed | True
Villamor, AJ | Review and Messaging | View Feedback | 2025-10-31 | CASE-038 | User leaves required field empty | Fails with error message | Performed as expected | Passed | True
Villamor, AJ | Review and Messaging | View Feedback | 2025-10-31 | CASE-039 | User enters valid data | Operation successful | Performed as expected | Passed | True
Villamor, AJ | Review and Messaging | In-App Chat | 2025-10-31 | CASE-040 | User enters invalid input | Fails with error message | Performed as expected | Passed | True
Villamor, AJ | Review and Messaging | In-App Chat | 2025-10-31 | CASE-041 | User leaves required field empty | Fails with error message | Performed as expected | Passed | True
Villamor, AJ | Review and Messaging | In-App Chat | 2025-10-31 | CASE-042 | User enters valid data | Operation successful | Performed as expected | Passed | True
Villamor, AJ | Account Management | Login Validation | 2025-11-02 | CASE-043 | LoginRequest validates email and password format | Invalid email format should fail validation | Performed as expected | Passed | True
Villamor, AJ | Account Management | Profile Update | 2025-11-02 | CASE-044 | Profile email is lowercased automatically | Mixed case email normalized to lowercase | Performed as expected | Passed | True
Villamor, AJ | Account Management | Profile Update | 2025-11-02 | CASE-045 | Email must be unique across users | Duplicate email rejected with validation error | Performed as expected | Passed | True
Villamor, AJ | Account Management | Profile Update | 2025-11-02 | CASE-046 | Profile picture max size validation (5MB) | Files over 5MB rejected | Performed as expected (skipped if GD missing) | Passed | True
Villamor, AJ | Job Management | Post Job | 2025-11-02 | CASE-047 | Description minimum 100 chars boundary test | Exactly 100 chars should pass validation | Performed as expected | Passed | True
Villamor, AJ | Job Management | Post Job | 2025-11-02 | CASE-048 | Budget minimum boundary test (min:5) | Budget below 5 should fail validation | Performed as expected | Passed | True
Villamor, AJ | Job Management | Post Job | 2025-11-02 | CASE-049 | Skills_requirements auto-generated from required_skills | When skills_requirements missing, auto-populate from required_skills | Performed as expected (Fixed CASE-012 bug) | Passed | True
Abordo, Nykrow | Bidding Module | Submit Bid | 2025-11-02 | CASE-050 | Proposal message minimum 50 chars boundary | Exactly 50 chars should pass | Performed as expected | Passed | True
Abordo, Nykrow | Bidding Module | Submit Bid | 2025-11-02 | CASE-051 | Proposal message under 50 chars rejected | 49 chars should fail validation | Performed as expected | Passed | True
Villamor, AJ | Account Management | Login Security | 2025-11-02 | CASE-052 | Rate limiting locks after 5 failed attempts | 6th attempt blocked by rate limiter | Performed as expected | Passed | True
Villamor, AJ | Account Management | Login Security | 2025-11-02 | CASE-053 | Rate limit cleared after successful login | Failed attempts counter reset on success | Performed as expected | Passed | True
Villamor, AJ | Account Management | Login Security | 2025-11-02 | CASE-054 | Remember-me sets recaller cookie | Cookie starting with remember_web_ present | Performed as expected | Passed | True
Villamor, AJ | Job Management | Post Job | 2025-11-02 | CASE-055 | Only employers can create jobs | Gig workers cannot create jobs | Performed as expected | Passed | True
Abordo, Nykrow | Bidding Module | Manage Proposals | 2025-11-02 | CASE-056 | Only job owner can accept/reject bids | Other employers cannot modify bids | Performed as expected | Passed | True
Abordo, Nykrow | Bidding Module | View Bids | 2025-11-02 | CASE-057 | Bid visibility restricted to owner and worker | Other users get 403 forbidden | Performed as expected | Passed | True
Villamor, AJ | AI Matching | Job Matching Service | 2025-11-02 | CASE-058 | Required skills weighted higher than preferred | Worker with required skill scores higher | Performed as expected | Passed | True
Villamor, AJ | Profile | Profile Completion | 2025-11-02 | CASE-059 | Non-gig workers always 100% complete | Employers show 100% completion | Performed as expected | Passed | True
Villamor, AJ | Profile | Profile Completion | 2025-11-02 | CASE-060 | Profile completion percentage updates dynamically | Missing fields count decreases as fields filled | Performed as expected | Passed | True
Abordo, Nykrow | Contract Management | Create Contract | 2025-11-02 | CASE-061 | Accepting bid creates project, transaction, contract | All three entities created atomically | Performed as expected | Passed | True
Abordo, Nykrow | Contract Management | Create Contract | 2025-11-02 | CASE-062 | Accepting bid fails with insufficient escrow | Error when escrow balance too low | Performed as expected | Passed | True
Abordo, Nykrow | Database Integrity | Bid Constraints | 2025-11-02 | CASE-063 | Unique constraint on (job_id, gig_worker_id) | Duplicate bid throws QueryException | Performed as expected | Passed | True
Villamor, AJ | Profile | Profile Picture Upload | 2025-11-02 | CASE-064 | Profile picture uploads to R2 and deletes old | New file stored, old file deleted | Performed as expected (skipped if GD missing) | Passed | True
Villamor, AJ | Notifications | Email Verification | 2025-11-02 | CASE-065 | Verify email reminder not duplicated | Only one unread reminder sent | Skipped (environment-dependent) | Skipped | True
Abordo, Nykrow | Payment Integration | Stripe Webhook | 2025-11-02 | CASE-066 | Stripe webhook rejects invalid signature | Returns 400/401/403 for bad signature | Performed as expected | Passed | True
Villamor, AJ | Account Management | OAuth Login | 2025-11-02 | CASE-067 | Google OAuth redirect endpoint protected | GET request allowed, redirects or 404 | Performed as expected | Passed | True
Villamor, AJ | Performance | Jobs Listing | 2025-11-02 | CASE-068 | Jobs index has reasonable query count | Query count under threshold (<=40) | Performed as expected | Passed | True
Villamor, AJ | Validation | Email Rules | 2025-11-02 | CASE-069 | Email validation accepts mixed case | MiXeD@Example.COM passes validation | Performed as expected | Passed | True
Villamor, AJ | Validation | Date Rules | 2025-11-02 | CASE-070 | Deadline after:today respects timezone | Tomorrow passes, today fails | Performed as expected | Passed | True
Villamor, AJ | Data Sanitization | Skills/Languages | 2025-11-02 | CASE-071 | Random skills/languages arrays sanitized | Various array formats accepted without error | Performed as expected (10 iterations) | Passed | True
Villamor, AJ | Account Management | Login Validation | 2025-11-02 | CASE-043 | LoginRequest validates email and password format | Invalid email format should fail validation | Performed as expected | Passed | True
Villamor, AJ | Account Management | Profile Update | 2025-11-02 | CASE-044 | Profile email is lowercased automatically | Mixed case email normalized to lowercase | Performed as expected | Passed | True
Villamor, AJ | Account Management | Profile Update | 2025-11-02 | CASE-045 | Email must be unique across users | Duplicate email rejected with validation error | Performed as expected | Passed | True
Villamor, AJ | Account Management | Profile Update | 2025-11-02 | CASE-046 | Profile picture max size validation (5MB) | Files over 5MB rejected | Performed as expected (skipped if GD missing) | Passed | True
Villamor, AJ | Job Management | Post Job | 2025-11-02 | CASE-047 | Description minimum 100 chars boundary test | Exactly 100 chars should pass validation | Performed as expected | Passed | True
Villamor, AJ | Job Management | Post Job | 2025-11-02 | CASE-048 | Budget minimum boundary test (min:5) | Budget below 5 should fail validation | Performed as expected | Passed | True
Villamor, AJ | Job Management | Post Job | 2025-11-02 | CASE-049 | Skills_requirements auto-generated from required_skills | When skills_requirements missing, auto-populate from required_skills | Performed as expected (Fixed CASE-012 bug) | Passed | True
Abordo, Nykrow | Bidding Module | Submit Bid | 2025-11-02 | CASE-050 | Proposal message minimum 50 chars boundary | Exactly 50 chars should pass | Performed as expected | Passed | True
Abordo, Nykrow | Bidding Module | Submit Bid | 2025-11-02 | CASE-051 | Proposal message under 50 chars rejected | 49 chars should fail validation | Performed as expected | Passed | True
Villamor, AJ | Account Management | Login Security | 2025-11-02 | CASE-052 | Rate limiting locks after 5 failed attempts | 6th attempt blocked by rate limiter | Performed as expected | Passed | True
Villamor, AJ | Account Management | Login Security | 2025-11-02 | CASE-053 | Rate limit cleared after successful login | Failed attempts counter reset on success | Performed as expected | Passed | True
Villamor, AJ | Account Management | Login Security | 2025-11-02 | CASE-054 | Remember-me sets recaller cookie | Cookie starting with remember_web_ present | Performed as expected | Passed | True
Villamor, AJ | Job Management | Post Job | 2025-11-02 | CASE-055 | Only employers can create jobs | Gig workers cannot create jobs | Performed as expected | Passed | True
Abordo, Nykrow | Bidding Module | Manage Proposals | 2025-11-02 | CASE-056 | Only job owner can accept/reject bids | Other employers cannot modify bids | Performed as expected | Passed | True
Abordo, Nykrow | Bidding Module | View Bids | 2025-11-02 | CASE-057 | Bid visibility restricted to owner and worker | Other users get 403 forbidden | Performed as expected | Passed | True
Villamor, AJ | AI Matching | Job Matching Service | 2025-11-02 | CASE-058 | Required skills weighted higher than preferred | Worker with required skill scores higher | Performed as expected | Passed | True
Villamor, AJ | Profile | Profile Completion | 2025-11-02 | CASE-059 | Non-gig workers always 100% complete | Employers show 100% completion | Performed as expected | Passed | True
Villamor, AJ | Profile | Profile Completion | 2025-11-02 | CASE-060 | Profile completion percentage updates dynamically | Missing fields count decreases as fields filled | Performed as expected | Passed | True
Abordo, Nykrow | Contract Management | Create Contract | 2025-11-02 | CASE-061 | Accepting bid creates project, transaction, contract | All three entities created atomically | Performed as expected | Passed | True
Abordo, Nykrow | Contract Management | Create Contract | 2025-11-02 | CASE-062 | Accepting bid fails with insufficient escrow | Error when escrow balance too low | Performed as expected | Passed | True
Abordo, Nykrow | Database Integrity | Bid Constraints | 2025-11-02 | CASE-063 | Unique constraint on (job_id, gig_worker_id) | Duplicate bid throws QueryException | Performed as expected | Passed | True
Villamor, AJ | Profile | Profile Picture Upload | 2025-11-02 | CASE-064 | Profile picture uploads to R2 and deletes old | New file stored, old file deleted | Performed as expected (skipped if GD missing) | Passed | True
Villamor, AJ | Notifications | Email Verification | 2025-11-02 | CASE-065 | Verify email reminder not duplicated | Only one unread reminder sent | Skipped (environment-dependent) | Skipped | True
Abordo, Nykrow | Payment Integration | Stripe Webhook | 2025-11-02 | CASE-066 | Stripe webhook rejects invalid signature | Returns 400/401/403 for bad signature | Performed as expected | Passed | True
Villamor, AJ | Account Management | OAuth Login | 2025-11-02 | CASE-067 | Google OAuth redirect endpoint protected | GET request allowed, redirects or 404 | Performed as expected | Passed | True
Villamor, AJ | Performance | Jobs Listing | 2025-11-02 | CASE-068 | Jobs index has reasonable query count | Query count under threshold (<=40) | Performed as expected | Passed | True
Villamor, AJ | Validation | Email Rules | 2025-11-02 | CASE-069 | Email validation accepts mixed case | MiXeD@Example.COM passes validation | Performed as expected | Passed | True
Villamor, AJ | Validation | Date Rules | 2025-11-02 | CASE-070 | Deadline after:today respects timezone | Tomorrow passes, today fails | Performed as expected | Passed | True
Villamor, AJ | Data Sanitization | Skills/Languages | 2025-11-02 | CASE-071 | Random skills/languages arrays sanitized | Various array formats accepted without error | Performed as expected (10 iterations) | Passed | True
Rachel Palacat | Admin Operations | Authorization | 2025-11-02 | CASE-072 | Non-admin users cannot access admin dashboard | Redirected or 403 Forbidden | Performed as expected | Passed | True
Rachel Palacat | Admin Operations | Authorization | 2025-11-02 | CASE-073 | Admin middleware protects admin routes | Access denied to admin routes | Performed as expected | Passed | True
Rachel Palacat | Admin Operations | Authorization | 2025-11-02 | CASE-074 | Admin user can access admin dashboard | Successfully accesses admin dashboard | Performed as expected | Passed | True
Rachel Palacat | Admin Operations | Authorization | 2025-11-02 | CASE-075 | Admin role persists across sessions | Admin status maintained after login | Performed as expected | Passed | True
Rachel Palacat | Admin Operations | User Management | 2025-11-02 | CASE-076 | Admin views all users list | Returns list of all users | Performed as expected | Passed | True
Rachel Palacat | Admin Operations | User Management | 2025-11-02 | CASE-077 | Admin views specific user details | Shows complete user information | Performed as expected | Passed | True
Rachel Palacat | Admin Operations | User Management | 2025-11-02 | CASE-078 | Admin updates user status successfully | User status updated in database | Performed as expected | Passed | True
Rachel Palacat | Admin Operations | User Management | 2025-11-02 | CASE-079 | Admin updates user with invalid status | Validation error or redirect | Performed as expected | Passed | True
Rachel Palacat | Admin Operations | User Management | 2025-11-02 | CASE-080 | Admin suspends user account | User status changed to suspended | Performed as expected | Passed | True
Rachel Palacat | Admin Operations | User Management | 2025-11-02 | CASE-081 | Admin activates suspended user | User status changed to active | Performed as expected | Passed | True
Rachel Palacat | Admin Operations | User Management | 2025-11-02 | CASE-082 | Admin deletes user with active projects | Cascades deletion or shows error | Performed as expected | Passed | True
Rachel Palacat | Admin Operations | User Management | 2025-11-02 | CASE-083 | Admin filters users by type | Returns only matching user types | Performed as expected | Passed | True
Rachel Palacat | Admin Operations | User Management | 2025-11-02 | CASE-084 | Admin bulk suspends multiple users | All users suspended atomically | Performed as expected | Passed | True
Rachel Palacat | Admin Operations | User Management | 2025-11-02 | CASE-085 | Admin cannot delete own account | Operation prevented with error | Performed as expected | Passed | True
Rachel Palacat | Admin Operations | ID Verification | 2025-11-02 | CASE-086 | Admin views pending verification requests | Lists all unverified requests | Performed as expected | Passed | True
Rachel Palacat | Admin Operations | ID Verification | 2025-11-02 | CASE-087 | Admin approves ID verification | User marked as verified | Performed as expected | Passed | True
Rachel Palacat | Admin Operations | ID Verification | 2025-11-02 | CASE-088 | Admin rejects ID verification with reason | Verification rejected, reason recorded | Performed as expected | Passed | True
Rachel Palacat | Admin Operations | ID Verification | 2025-11-02 | CASE-089 | Admin rejects verification without reason | Validation error or redirect | Performed as expected | Passed | True
Rachel Palacat | Admin Operations | ID Verification | 2025-11-02 | CASE-090 | Admin views verification document | Document displayed or downloaded | Performed as expected | Passed | True
Rachel Palacat | Admin Operations | ID Verification | 2025-11-02 | CASE-091 | Admin requests additional documentation | User notified to submit more docs | Performed as expected | Passed | True
Rachel Palacat | Admin Operations | ID Verification | 2025-11-02 | CASE-092 | Admin approves already verified user | No change or informative message | Performed as expected | Passed | True
Rachel Palacat | Admin Operations | ID Verification | 2025-11-02 | CASE-093 | Admin filters verifications by status | Returns matching verifications | Performed as expected | Passed | True
Rachel Palacat | Admin Operations | ID Verification | 2025-11-02 | CASE-094 | Admin views verification history | Shows complete verification timeline | Performed as expected | Passed | True
Rachel Palacat | Admin Operations | ID Verification | 2025-11-02 | CASE-095 | Admin exports verification reports | CSV/Excel export generated | Performed as expected | Passed | True
Rachel Palacat | Admin Operations | Fraud Detection | 2025-11-02 | CASE-096 | Admin views flagged accounts | Lists all flagged accounts | Performed as expected | Passed | True
Rachel Palacat | Admin Operations | Fraud Detection | 2025-11-02 | CASE-097 | Admin investigates fraud case | Shows detailed investigation data | Performed as expected | Passed | True
Rachel Palacat | Admin Operations | Fraud Detection | 2025-11-02 | CASE-098 | Admin marks fraud case as resolved | Case status updated to resolved | Performed as expected | Passed | True
Rachel Palacat | Admin Operations | Fraud Detection | 2025-11-02 | CASE-099 | Admin permanently bans fraudulent user | User permanently banned from platform | Performed as expected | Passed | True
Rachel Palacat | Admin Operations | Fraud Detection | 2025-11-02 | CASE-100 | Admin updates fraud case invalid status | Validation error or safe handling | Performed as expected | Passed | True
Rachel Palacat | Admin Operations | Fraud Detection | 2025-11-02 | CASE-101 | Admin views fraud detection metrics | Shows fraud statistics and trends | Performed as expected | Passed | True
Rachel Palacat | Admin Operations | Fraud Detection | 2025-11-02 | CASE-102 | Admin creates manual fraud alert | Fraud case created with alert | Performed as expected | Passed | True
Rachel Palacat | Admin Operations | Fraud Detection | 2025-11-02 | CASE-103 | Admin reviews transaction patterns | Transaction analysis displayed | Performed as expected | Passed | True
Rachel Palacat | Admin Operations | Fraud Detection | 2025-11-02 | CASE-104 | Admin links related fraud cases | Cases linked in system | Performed as expected | Passed | True
Rachel Palacat | Admin Operations | Security Testing | 2025-11-02 | CASE-105 | Admin panel protected against XSS | Malicious scripts sanitized | Performed as expected | Passed | True
Rachel Palacat | Admin Operations | Security Testing | 2025-11-02 | CASE-106 | Admin actions require CSRF token | Request rejected with 419 error | Performed as expected | Passed | True
Rachel Palacat | Admin Operations | Security Testing | 2025-11-02 | CASE-107 | Admin actions logged for audit | Action recorded in audit log | Performed as expected | Passed | True
Rachel Palacat | Admin Operations | Security Testing | 2025-11-02 | CASE-108 | Concurrent admin updates handled safely | No race conditions or data loss | Performed as expected | Passed | True
Rachel Palacat | Admin Operations | Security Testing | 2025-11-02 | CASE-109 | Admin export prevents SQL injection | Malicious SQL neutralized | Performed as expected | Passed | True